## Sheet1
issue id 1-21 is for without login
22-30 is for logged in as dealer
31- is for logged in as distributor(27,28,29 is also for distributor)
add more data for users, products, testimonials etc..
QA Defect & Issue Tracker
End-to-end defect tracking, triage, and resolution monitoring
TOTAL ISSUES |  | OPEN ISSUES |  | CRITICAL / BLOCKERS |  |  | RESOLUTION RATE
32 |  | 32 |  | 0 |  |  | 0%
Issue ID | Summary | Placement / Module | Issue Type | Severity | Priority | Status | Assigned To | Expected | Evidence / Link
1 | Swip to next | First page when we open the app | UI/Display | Minor | P3 - Low | Open | Vira | user should be able to slide left right on touch
2 | change images | home section | UI/Display | Minor | P3 - Low | Open | Vira | relevant images
3 | remove CEAT in orange | home section | UI/Display | Moderate | P2 - Medium | Open | Vira | no CEAT mention anywhere in the app
4 | remove "new" in orange after 7 days of the product launch | product section | Functional | Moderate | P3 - Low | Open
5 | change images | product section | UI/Display | Minor | P3 - Low | Open | vira | relevant images
6 | remove tires and tracks | products->skid steer tires | UI/Display | Major | P1 - High | Open | vira | we are already in product section of skid and steer tires then why again tires and tracks section on top
7 | reset filters | products->skid steer tires->new | UI/Display, Backend | Major | P1 - High | Open | vira,aary | reset filter should be there in sort for all, new, featured
8 | sign in pop up |  | UI/Display | Minor | P3 - Low | Open | vira | sign in pop up should dissapear by sliding to right, not down
9 | no data in key features,applications,compatible equipment | products->skid steer tires->xtr 770 | Backend | Major | P1 - High | Open | aary | filled correct data
10 | same info 3 times(header, specs, dimensions) on same page | products->skid steer tires->xtr 770 | UI/Display | Moderate | P2 - Medium | Open | vira | same info like max load, max speed should not be shown 3 times
11 | share feature not working | products->skid steer tires->xtr 770 | Functional, Backend | Major | P1 - High | Open | aary | on clicking on share button it should ask to share using whatsapp etc options. and then redirect to whatsapp(or other app which we user has selected)
12 | rating stars not matching the rating | products->skid steer tires->xtr 770 | UI/Display | Minor | P3 - Low | Open | vira | the star rating should match the actual rating like for 4.5 only 4 and half stars should be filled
13 | gramatical mistake | products->telehandler tires | UI/Display | Moderate | P3 - Low | Open | vira | if there is only one product then it should show "1 product" and not "1 products". sme for results
14 | we have zoom out always when we click on any of the dealer block | find a dealer |  | Major | P1 - High | Open |  | whenever we click on any dealer block then it should show on maps in proper view.
15 | showing error | bookmarks | UI/Display | Major | P2 - Medium | Open | vira | to bookmark anything, login is required. so the page should ask to login first. dont show the error
16 | call and email not working | contact support | Functional, Backend | Major | P1 - High | Open | aary | when clicled on call or email it should open the phone and gmail
17 | add option to copy phone no. and email | contact support | UI/Display, Backend | Major | P1 - High | Open | vira, aary | the user should be able to copy the phone number and the email given above.
18 | remove constomer story, NA and verified | testimonials->customer stories | UI/Display | Major | P2 - Medium | Open | vira | when we are already inside the customer story section then it should not show customer story again and again
19 | call and email not working + copy ph no. and email | support->distributor | UI/Display, Backend, Functional | Major | P1 - High | Open | vira, aary | when clicled on call or email it should open the phone and gmail and the user should be able to copy the ph no. and the email
20 | dealers anddistributor specific resources is not showing relevant things | support->role specific resources | Backend | Major | P1 - High | Open | aary | it sould show dealer specific resources like documents for only dealers in this. when clicked in that "dealer portal and locator"(rename this to "dealer resources") first it should ask for sign in just like it asks for employee and oem partner. same for distriibutor
21 | we are able to download documents from document library | support->document library | Backend, UI/Display | Major | P1 - High | Open | aary and vira | when clicked on that document we should be able to read the document but to download it should ask for sign in
22 | remove oem partner and employee portal | support | UI/Display | Minor | P3 - Low | Open | vira | oem partner and distributor should not be shown to the dealer
23 | directing to wrong page when clicked on dealer portal and locator | support->role specific resources | UI/Display, Backend | Major | P1 - High | Open | vira , aary | the dealer specific resources shold not redirect to the dealer locator page
24 | remove admin only document | support->document library | Backend | Major | P1 - High | Open | aary | the admin specific things should be shown only to admin
25 | added bookmarks of products, documents and stories are not visible in bookmarks section | bookmarks | Backend | Major | P1 - High | Open | aary | the dealer can see his bookmarked things
26 | access token expired error after sometime | bookmarks | Backend | Major | P1 - High | Open | aary | access token expired error after sometime
27 | cannot see the given feedback, viewd products, downloaded documents etc..(bookmark, searched). same for distributor(signed in as distributor). | profile->account activity & saved calculations | UI/Display, Backend | Major | P2 - Medium | Open | aary, vira | the dealer should be able to see his activity
28 | cannot see the calculations done by the dealer. same for distributor. | profile->account activity & saved calculations | Backend, UI/Display | Major | P2 - Medium | Open | vira,aary | the dealer should be able to see his activity
29 | blank screen. same for distributor | profile->language | Backend | Major | P1 - High | Open | aary | direct to the language page and show the languages options
30 | spacing between bookmarks/unread alerts and authorized dealer portal | profile | UI/Display | Minor | P3 - Low | Open | vira | the spacing sould be proper
31 | invalid business access token error | profile->reginal distributor portal | Backend | Major | P1 - High | Open | aary | it should show the distributor distrubutor portal
32